## Defect Report
ParaBank — Defect Report
Defect ID | Module | TC ID | Defect Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By | Reported Date | Fixed Date | Build Version
DID001 | Login | LI02 | Login succeeds with invalid username | 1.Open URL 2.Enter wrong username 3.Enter correct password 4.Click LOG IN | Error message should be shown | No error shown, user redirected to dashboard | High | High | Fixed | Babusingh | 01-Mar-2022 | 05-Mar-2022 | v1.0
DID002 | Login | LI04 | No validation on empty username field | 1.Open URL 2.Leave username blank 3.Enter password 4.Click LOG IN | Error: 'Please enter a username' | No error shown | High | High | Fixed | Babusingh | 01-Mar-2022 | 05-Mar-2022 | v1.0
DID003 | Login | LI05 | No validation on empty password field | 1.Open URL 2.Enter username 3.Leave password blank 4.Click LOG IN | Error: 'Please enter a password' | No error shown | High | High | Fixed | Babusingh | 01-Mar-2022 | 05-Mar-2022 | v1.0
DID004 | Login | LI07 | Username field is not case sensitive | 1.Open URL 2.Enter username in UPPERCASE 3.Enter password 4.Click LOG IN | Error: username not found | Login succeeds with uppercase username | Medium | Medium | Open | Babusingh | 01-Mar-2022 |  | v1.0
DID005 | Login | LI08 | Special characters accepted in username | 1.Enter @#$% in username field 2.Enter password 3.Click LOG IN | Validation error should be shown | No validation, proceeds to login attempt | Medium | Medium | Open | Babusingh | 01-Mar-2022 |  | v1.0
DID006 | Register | RG02 | Empty First Name field not validated | 1.Open Register page 2.Leave First Name blank 3.Fill other fields 4.Click Register | Error: 'First name is required' | No error, form submits | High | High | Fixed | Babusingh | 02-Mar-2022 | 06-Mar-2022 | v1.0
DID007 | Register | RG12 | Mismatched password not validated properly | 1.Open Register page 2.Enter password: Test@1234 3.Enter confirm: Different@1234 4.Click Register | Error: 'Passwords did not match' | Generic error shown without clear message | Medium | High | Fixed | Babusingh | 02-Mar-2022 | 06-Mar-2022 | v1.0
DID008 | Register | RG13 | Duplicate username allows registration | 1.Open Register page 2.Enter existing username: testuser123 3.Fill other fields 4.Click Register | Error: 'This username already exists' | System allows duplicate username registration | High | High | Open | Babusingh | 02-Mar-2022 |  | v1.0
DID009 | Register | RG14 | Numeric values accepted in First Name | 1.Open Register page 2.Enter 12345 in First Name 3.Fill other fields 4.Click Register | Validation error should be shown | System accepts numeric first name | Medium | Medium | Open | Babusingh | 02-Mar-2022 |  | v1.0
DID010 | Register | RG16 | Invalid Zip Code not validated | 1.Open Register page 2.Enter ABCDE in Zip Code 3.Fill other fields 4.Click Register | Error: 'Zip Code is invalid' | No validation error shown | Medium | Medium | In Progress | Babusingh | 02-Mar-2022 |  | v1.0
DID011 | Transfer Funds | TF02 | Empty amount field not validated | 1.Login 2.Go to Transfer Funds 3.Leave amount blank 4.Click Transfer | Error: 'The amount cannot be empty' | No error shown, blank transfer attempted | High | High | Fixed | Babusingh | 03-Mar-2022 | 07-Mar-2022 | v1.0
DID012 | Transfer Funds | TF03 | Zero amount transfer allowed | 1.Login 2.Go to Transfer Funds 3.Enter 0 in amount 4.Click Transfer | Error: 'Please enter a valid amount' | Transfer of 0 amount succeeds | High | High | Fixed | Babusingh | 03-Mar-2022 | 07-Mar-2022 | v1.0
DID013 | Transfer Funds | TF04 | Negative amount transfer not blocked | 1.Login 2.Go to Transfer Funds 3.Enter -100 in amount 4.Click Transfer | Error: 'Please enter a valid amount' | Negative transfer accepted | High | High | Open | Babusingh | 03-Mar-2022 |  | v1.0
DID014 | Transfer Funds | TF05 | Alphabets accepted in amount field | 1.Login 2.Go to Transfer Funds 3.Enter 'abc' in amount 4.Click Transfer | Validation error should be shown | No client-side validation on amount field | Medium | High | In Progress | Babusingh | 03-Mar-2022 |  | v1.0
DID015 | Transfer Funds | TF07 | Transfer amount more than balance not blocked | 1.Login 2.Go to Transfer Funds 3.Enter 999999 in amount 4.Click Transfer | Error: 'Insufficient funds' | Transfer succeeds even with insufficient balance | Critical | High | Open | Babusingh | 03-Mar-2022 |  | v1.0
DID016 | Bill Pay | BP02 | Empty Payee Name not validated | 1.Login 2.Go to Bill Pay 3.Leave Payee Name blank 4.Click Send Payment | Error: 'Payee name is required' | No validation error shown | High | High | Fixed | Babusingh | 04-Mar-2022 | 08-Mar-2022 | v1.0
DID017 | Bill Pay | BP09 | Empty amount in Bill Pay not validated | 1.Login 2.Go to Bill Pay 3.Leave Amount blank 4.Click Send Payment | Error: 'The amount cannot be empty' | Form submits without validation | High | High | Fixed | Babusingh | 04-Mar-2022 | 08-Mar-2022 | v1.0
DID018 | Bill Pay | BP10 | Zero amount bill payment allowed | 1.Login 2.Go to Bill Pay 3.Enter 0 in amount 4.Click Send Payment | Error: 'Please enter a valid amount' | Payment of 0 amount succeeds | Medium | High | Open | Babusingh | 04-Mar-2022 |  | v1.0
DID019 | Find Transactions | FT02 | Invalid transaction ID shows no error | 1.Login 2.Go to Find Transactions 3.Enter invalid ID: 99999999 4.Click Find | Error: 'No transaction found' | Blank result page shown without message | Medium | Medium | Open | Babusingh | 05-Mar-2022 |  | v1.0
DID020 | Find Transactions | FT04 | Invalid date format accepted | 1.Login 2.Go to Find Transactions 3.Enter 'abc' in date field 4.Click Find | Validation error for invalid date format | No validation, blank results shown | Medium | Medium | Open | Babusingh | 05-Mar-2022 |  | v1.0
DID021 | Find Transactions | FT06 | Invalid date range not validated | 1.Login 2.Go to Find Transactions 3.Enter To date before From date 4.Click Find | Error or no results with message | Results shown without error message | Low | Low | Open | Babusingh | 05-Mar-2022 |  | v1.0
DID022 | Update Contact Info | UC02 | Empty First Name not validated on update | 1.Login 2.Go to Update Contact Info 3.Clear First Name 4.Click Update | Error: 'First name is required' | Profile updated with empty First Name | High | High | Fixed | Babusingh | 06-Mar-2022 | 09-Mar-2022 | v1.0
DID023 | Update Contact Info | UC12 | Invalid Zip Code accepted on update | 1.Login 2.Go to Update Contact Info 3.Enter ABCDE in Zip Code 4.Click Update | Error: 'Zip Code is invalid' | Profile updated with invalid Zip Code | Medium | Medium | In Progress | Babusingh | 06-Mar-2022 |  | v1.0
DID024 | Update Contact Info | UC13 | Special characters accepted in name fields | 1.Login 2.Go to Update Contact Info 3.Enter @#$% in First Name 4.Click Update | Validation error should be shown | Profile updated with special characters | Medium | Medium | Open | Babusingh | 06-Mar-2022 |  | v1.0
DID025 | Request Loan | RL02 | Empty loan amount not validated | 1.Login 2.Go to Request Loan 3.Leave loan amount blank 4.Click Apply Now | Error: 'Loan amount is required' | No validation error shown | High | High | Fixed | Babusingh | 07-Mar-2022 | 10-Mar-2022 | v1.0
DID026 | Request Loan | RL04 | Zero loan amount accepted | 1.Login 2.Go to Request Loan 3.Enter 0 in loan amount 4.Click Apply Now | Error: 'Please enter a valid amount' | Loan application submitted with 0 amount | High | High | Open | Babusingh | 07-Mar-2022 |  | v1.0
DID027 | Request Loan | RL05 | Alphabets accepted in loan amount | 1.Login 2.Go to Request Loan 3.Enter 'abc' in loan amount 4.Click Apply Now | Validation error should be shown | No client-side validation | Medium | Medium | Open | Babusingh | 07-Mar-2022 |  | v1.0
DID028 | Request Loan | RL06 | Negative loan amount not blocked | 1.Login 2.Go to Request Loan 3.Enter -1000 in loan amount 4.Click Apply Now | Error: 'Please enter a valid amount' | Loan application proceeds with negative amount | High | High | Open | Babusingh | 07-Mar-2022 |  | v1.0
DID029 | Open New Account | OA09 | Initial balance not reflecting correctly | 1.Login 2.Open new account 3.Check new account balance | Initial balance should reflect minimum deposit | Balance shown as 0 instead of minimum deposit amount | Medium | Medium | In Progress | Babusingh | 08-Mar-2022 |  | v1.0
DID030 | Accounts Overview | AO06 | Total balance calculation incorrect | 1.Login 2.Open multiple accounts 3.Check total balance in Accounts Overview | Total should be sum of all account balances | Total balance shows incorrect sum | High | High | Open | Babusingh | 08-Mar-2022 |  | v1.0

## Summary
Defect Summary
By Status
Status | Count | % of Total
Fixed | 11 | 36.7%
Open | 15 | 50.0%
In Progress | 4 | 13.3%
By Severity
Severity | Count | % of Total
High | 15 | 50.0%
Medium | 13 | 43.3%
Critical | 1 | 3.3%
Low | 1 | 3.3%